## WBS
WBS ID | Level | Task / Deliverable | Description | Owner | Status
1.0 | 1 | Hospital Management System Mini Project | Overall project | Team H-12 | Planned
1.1 | 2 | Requirements Engineering | Identify and document system requirements | Team H-12 | Planned
1.1.1 | 3 | SRS Preparation | Prepare Software Requirements Specification | Team H-12 | Completed
1.1.2 | 3 | Functional Requirements | Document FRs for authentication, patients, doctors, appointments and reporting | Team H-12 | Completed
1.1.3 | 3 | Non-Functional Requirements | Document performance, reliability, security and maintainability requirements | Team H-12 | Completed
1.1.4 | 3 | Requirements Traceability Matrix | Map requirements to test cases | Team H-12 | In Progress
1.2 | 2 | System Design | Define architecture, components and database design | Team H-12 | In Progress
1.2.1 | 3 | Architecture Design | 3-tier layered architecture | Team H-12 | Completed
1.2.2 | 3 | Component Design | Define UI, BLL and DAL components | Team H-12 | Completed
1.2.3 | 3 | Database Design | Design SQLite entities and relationships | Team H-12 | Completed
1.2.4 | 3 | Use Case / Sequence Design | Create behavioural UML diagrams | Team H-12 | Planned
1.3 | 2 | Implementation | Develop the C/C++ console-based HMS | Team H-12 | Planned
1.3.1 | 3 | Authentication Module | Login, roles, failed-attempt handling and logout | Team H-12 | Planned
1.3.2 | 3 | Patient Module | Patient registration, search and update | Team H-12 | Planned
1.3.3 | 3 | Doctor Module | Doctor registration, specialization and availability | Team H-12 | Planned
1.3.4 | 3 | Appointment Module | Booking, conflict checking, cancellation and rescheduling | Team H-12 | Planned
1.3.5 | 3 | Reporting Module | Generate appointment and patient reports | Team H-12 | Planned
1.4 | 2 | Testing | Verify functional, integration, system and security behaviour | Team H-12 | In Progress
1.4.1 | 3 | Unit Testing | Test backend/module logic | Team H-12 | Planned
1.4.2 | 3 | Integration Testing | Test interactions between modules and DAL | Team H-12 | Planned
1.4.3 | 3 | System Testing | Test complete console workflows | Team H-12 | Planned
1.4.4 | 3 | Security Testing | Test authentication and SQL injection prevention | Team H-12 | Planned
1.4.5 | 3 | Performance / NFR Testing | Verify response time, memory and Valgrind requirements | Team H-12 | Planned
1.5 | 2 | AI-Assisted Bug Fixing | Use Copilot/AI tool for bug fix and patch verification | Team H-12 | Planned
1.6 | 2 | Deployment | Document environment setup and execution steps | Team H-12 | Planned
1.7 | 2 | Demo & Documentation | Prepare screenshots, video and final repository | Team H-12 | Planned